CC6004 Network and Cloud Security

Project Methodology Document

Multi-Layer Dynamic Shift Cipher (MLDSC)

Project Manager: Shivas Pillai (22008121)  |  Academic Year: 2025–26

# 1. Chosen Methodology — Agile / SCRUM

The group adopted an Agile methodology with SCRUM-inspired practices. Agile was chosen over a traditional Waterfall approach for the following reasons:

- The cipher design was exploratory — requirements evolved as the team learned more about cryptographic trade-offs during the literature review.

- A working prototype could be produced early (Sprint 1 alpha), then refined, rather than waiting until all design decisions were finalised.

- The group of 10 members benefits from short feedback cycles rather than long sequential phases.

- The assessment brief itself is iterative in structure — research informs design, design informs implementation, implementation informs evaluation.

Waterfall was considered but rejected because the cipher algorithm was not fully specified at project kick-off — a key precondition for Waterfall to be appropriate.

# 2. SCRUM Roles

| SCRUM Role | Assigned To | Responsibilities |
| --- | --- | --- |
| Product Owner | Shivas Pillai (22008121) | Defines and prioritises requirements; approves deliverables; final submission |
| SCRUM Master | Oluwademilade Soyoye (23055423) | Facilitates meetings; removes blockers; maintains sprint backlog |
| Development Team | All 10 members | Implements tasks assigned in each sprint; attends sprint reviews |

Table 1: SCRUM role assignments

# 3. Sprint Plan

## Sprint 1 — Foundation (3–14 February 2026)

Goal: Establish group structure; complete initial research; agree cipher concept.

| Task | Description | Owner | Status |
| --- | --- | --- | --- |
| Role assignment | Agree and document all 10 member roles | Shivas | DONE |
| Communication setup | Create WhatsApp group; OneDrive shared folder | Shivas | DONE |
| Research — classical | Read 2+ papers each on classical ciphers | Muzhgan, Ryan | DONE |
| Research — modern | Read AES, SHA-256, RSA primary sources | Dumitru, Abdullah | DONE |
| Cipher concept | Agree 3-layer MLDSC concept in writing | Dumitru | DONE |
| Requirements draft | First MoSCoW requirements list | Shivas, Demi | DONE |

Table 2: Sprint 1 backlog and completion

## Sprint 2 — Design and Prototype (17 February – 6 March 2026)

Goal: Produce full cipher specification and working Python alpha.

| Task | Description | Owner | Status |
| --- | --- | --- | --- |
| Algorithm spec | Write formal Layer 1/2/3 specification with maths | Dumitru | DONE |
| Key schedule design | Select SHA-256 chain; document rationale | Dumitru | DONE |
| Python alpha | Working encrypt/decrypt, no verbose mode yet | Dumitru, Gemechu | DONE |
| Flow diagrams v1 | Draft encryption and decryption flowcharts | Halima | DONE |
| Literature review | Complete Sections 2.1–2.5 draft | Muzhgan, Ryan | DONE |
| Sprint 2 review | Meeting 2 — demo alpha; approve spec | All | DONE |

Table 3: Sprint 2 backlog and completion

## Sprint 3 — Full Implementation and Report (9–27 March 2026)

Goal: Complete implementation with verbose mode; draft full report; build test suite.

| Task | Description | Owner | Status |
| --- | --- | --- | --- |
| Verbose mode | Add step-by-step table output to encrypt/decrypt | Dumitru | DONE |
| Test suite | Five black-box test cases; all must pass | Sabeeh | DONE |
| HTML demo | Interactive browser demo of all three layers | Dumitru | DONE |
| Report Sections 3–7 | Design, Implementation, Evaluation, Ethics, PM | Multiple | DONE |
| Diagrams final | Finalised flowcharts incorporated into report | Halima | DONE |
| Sprint 3 review | Meeting 3 — live demo; section review | All | DONE |

Table 4: Sprint 3 backlog and completion

## Sprint 4 — Finalisation and Submission (30 March – 25 April 2026)

Goal: Final report, peer assessment, presentation preparation, submission.

| Task | Description | Owner | Status |
| --- | --- | --- | --- |
| Report Sections 8–13 | Reflection, evaluation, recommendations, conclusion | Maarya, Demi, Sabeeh | DONE |
| Peer assessment forms | One form per member; all submitted individually | All members | DONE |
| Presentation slides | PowerPoint for in-class presentation | Halima | DONE |
| Final review | Meeting 4 — full report read-through; corrections | All | DONE |
| Submission | WebLearn Turnitin submission by 27 April | Shivas | DONE |

Table 5: Sprint 4 backlog and completion

# 4. Communication and Collaboration Tools

| Tool | Purpose | How Used |
| --- | --- | --- |
| WhatsApp Group | Informal daily communication | Quick questions, sharing links, confirming meeting times, sharing draft sections for quick review |
| Microsoft OneDrive | Document version control | Single shared folder for all report drafts; naming convention: "MLDSC_Report_vX.docx" |
| Microsoft Teams | Online meetings (Sprint 3) | Sprint 3 meeting held online when in-person attendance not possible for all members |
| Python + GitHub | Code development | Dumitru and Gemechu used GitHub for code version tracking; final version shared via OneDrive |
| WebLearn | Official submission portal | Final report submitted by Shivas Pillai; meeting minutes documented for tutor access if needed |

Table 6: Collaboration tools and usage

# 5. Risk Register

| Risk | Likelihood | Impact | Mitigation | Status |
| --- | --- | --- | --- | --- |
| Cipher mathematically incorrect | Low | High | Test suite with round-trip verification | Mitigated — all tests pass |
| Key member unavailable | Medium | Medium | Role overlap; meeting notes shared with all | Managed — Sprint 3 online |
| Submission deadline missed | Low | High | Internal deadline 27 Apr, one day early | On track |
| Plagiarism/similarity flag | Low | High | One submission only; Harvard refs; original code | Mitigated |
| Python version incompatibility | Low | Medium | Standard library only; tested Python 3.8–3.12 | Mitigated |

Table 7: Project risk register